Math Runner Project Backlog (with Days)

| User Story ID | User Story | Acceptance Criteria | Priority | Initial Estimate (days) | Adjustment Factor | Final Estimate (days) |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | As a player, I want to control my character so I can navigate the game world. | Player can move left, right, jump, and attack smoothly. | High | 2.5 | 0.8 | 2 |
| 1.2 | As a player, I want enemies to appear so that the game feels challenging. | Enemies spawn, move, attack, and collide with player. | High | 4 | 0.75 | 3 |
| 1.3 | As a player, I want the game to track my score and lives. | Score increments, lives decrease, high score saves to file. | High | 2 | 1.0 | 2 |
| 2.1 | As a player, I want math questions to appear when I face enemies. | Questions load, answers accepted, feedback shown. | High | 1.5 | 1.33 | 2 |
| 2.2 | As a player, I want hints to appear when I’m struggling. | Hints appear after repeated wrong answers or frustration. | Medium | 4 | 0.5 | 2 |
| 2.3 | As a player, I want the game to change difficulty dynamically. | Level changes when poor performance or hints triggered. | Medium | 2 | 1 | 2 |
| 3.1 | As a player, I want the game to detect my face emotion. | Webcam runs, emotion detected in real-time. | High | 10 | 0.6 | 6 |
| 3.2 | As a player, I want the game to react to frustration. | Bad emotion counter triggers hints or difficulty drop. | High | 5 | 0.6 | 3 |
| 4.1 | As a player, I want a menu system (Start, Options, About Us). | Menu buttons functional, About Us page loads. | Medium | 3 | 1.0 | 3 |
| 4.2 | As a player, I want smooth animations. | Player, enemy, and background animations run smoothly. | Medium | 3.2 | 1.25 | 4 |
| 5.1 | As a player, I want background music. | Music plays in menu and game, can pause/resume. | Medium | 2 | 0.5 | 1 |

Math Runne Sprint Backlog

| Release | Title | Sprint | User Story ID | User Story | Duration (days) | Dates (Start – End) |
| --- | --- | --- | --- | --- | --- | --- |
| Release 1 | Core Gameplay & Learning Mechanics | Sprint 1 | 1.1 | Control character (move, jump, attack) | 2 | Aug 10 – Aug 11 |
|  |  | Sprint 1 | 1.2 | Enemies spawn, move, attack | 3 | Aug 12 – Aug 14 |
|  |  | Sprint 1 | 1.3 | Track score and lives | 2 | Aug 15 – Aug 16 |
|  |  | Sprint 1 | 2.1 | Math questions on enemy encounters | 3 | Aug 17 – Aug 19 |
|  |  | Total Sprint 1 = 10 days |  |  |  | Aug 10 – Aug 19 |
| Release 2 | Core Gameplay & Learning Mechanics | Sprint 2 | 2.2 | Hints appear after struggles | 2 | Aug 20 – Aug 21 |
|  |  | Sprint 2 | 2.3 | Dynamic difficulty adjustment | 2 | Aug 22 – Aug 23 |
|  |  | Sprint 2 | 3.1 | Face emotion detection | 6 | Aug 24 – Aug 29 |
|  |  | Sprint 2 | 3.2 | React to frustration (hints/difficulty drop) | 3 | Aug 30 – Sept 1 |
|  |  | Total Sprint 2 = 13 days |  |  |  | Aug 20 – Sept 1 |
| Release 3 | User Experience & Enhancements | Sprint 3 | 4.1 | Menu system (Start, Options, About Us) | 3 | Sept 2 – Sept 4 |
|  |  | Sprint 3 | 4.2 | Smooth animations | 4 | Sept 5 – Sept 7 |
|  |  | Sprint 3 | 5.1 | Background music (pause/resume) | 1 | Sept 8 |
|  |  | Total Sprint 3 = 8 days |  |  |  | Sept 2 – Sept 8 |